## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
STT | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Login | Public Feature | Medium | Iteration 1 | SE130619, SE140424 | Nguyễn Hoàng Hồng Phúc,Nguyễn Xuân Khánh Hòa | Iteration 2
2 | Change Password | Public Feature | Simple | Iteration 1 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa | Iteration 3
3 | UploadCV | Student Feature | Complex | Iteration 3 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa | Iteration 3
4 | Apply For A Position | Student Feature | Medium | Iteration 2 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa | Iteration 3
5 | Confirm Application | Student Feature | Medium | Iteration 3 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa
6 | Lookup company detail and job description | Student Feature | Complex | Iteration 2 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa | Iteration 2
7 | Browse for jobs | Student Feature | Simple | Iteration 3 | SE130619, SE140424 | Nguyễn Hoàng Hồng Phúc,Nguyễn Xuân Khánh Hòa | Iteration 3
8 | Browse for company | Student Feature | Simple | Iteration 1 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa | Iteration 2
9 | Update Profile | Student Feature | Medium | Iteration 1 | SE150652, SE140424 | Phạm Trần Lê Bảo,Nguyễn Xuân Khánh Hòa
10 | View comany list | School Admin Feature | Simple | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 2
11 | View a specific company infomation | School Admin Feature | Simple | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 2
12 | Edit a specific company infomation | School Admin Feature | Medium | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 2
13 | Create a new Student | School Admin Feature | Simple | Iteration 2 | SE150652, SE150640 | Phạm Trần Lê Bảo,Nguyễn Đặng Trường Anh | Iteration 3
14 | Create new Company | School Admin Feature | Simple | Iteration 2 | SE150652, SE150640 | Phạm Trần Lê Bảo,Nguyễn Đặng Trường Anh | Iteration 3
15 | Import OJT student list (with Excel) | School Admin Feature | Complex | Iteration 3 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 3
16 | View Student List | School Admin Feature | Simple | Iteration 2 | SE130619, SE150640 | Nguyễn Hoàng Hồng Phúc,Nguyễn Đặng Trường Anh | Iteration 2
17 | View a specific student information | School Admin Feature | Simple | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 2
18 | View application status | School Admin Feature | Simple | Iteration 3 | SE130619, SE150640 | Nguyễn Hoàng Hồng Phúc, Nguyễn Đặng Trường Anh | Iteration 3
19 | Edit a specific student information | School Admin Feature | Medium | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 3
20 | Export student list | School Admin Feature | Medium | Iteration 3 | SE130496, SE140424 | Nguyễn Hiếu Nghĩa,Nguyễn Xuân Khánh Hòa
21 | Create a job for comany | Company Representative Feature | Medium | Iteration 2 | SE130496, SE140425 | Nguyễn Hiếu Nghĩa,Nguyễn Xuân Khánh Hòa
22 | Verify OJT Application | Company Representative Feature | Complex | Iteration 2 | SE130619, SE140424 | Nguyễn Hoàng Hồng Phúc,Nguyễn Đặng Trường Anh | Iteration 3
23 | View a specific student information | Company Representative Feature | Simple | Iteration 2 | SE130619, SE140425 | Nguyễn Hoàng Hồng Phúc,Nguyễn Xuân Khánh Hòa
24 | View student information list | Company Representative Feature | Simple | Iteration 2 | SE130619, SE140426 | Nguyễn Hoàng Hồng Phúc,Nguyễn Xuân Khánh Hòa | Iteration 3
25 | Offer for a specific student | Company Representative Feature | Medium | Iteration 3 | SE130496, SE140424 | Nguyễn Hiếu Nghĩa,Nguyễn Xuân Khánh Hòa
26 | Submit student's OJT result | Company Representative Feature | Medium | Iteration 3 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 3
27 | View company profile | Company Representative Feature | Simple | Iteration 2 | SE130496, SE150640 | Nguyễn Hiếu Nghĩa,Nguyễn Đặng Trường Anh | Iteration 2
28 | Edit company profile | Company Representative Feature | Medium | Iteration 2 | SE130619, SE150640 | Nguyễn Hoàng Hồng Phúc,Nguyễn Xuân Khánh Hòa | Iteration 3