## W1
PROJECT REPORT
Group | Journey
Week | 04/01/2021-08/01/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Research Project requirements | In Progress | - Define project requirements - Validate project requirements
2 | Research Project technologies | In Progress
3 | Work on documentation | In Progress
4 | Prototyping web screens | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Draw Context Diagram | All Members
2 | Make Product Backlog | PhucNHH
3 | Prototyping web screens | HoaNK & AnhNDT
4 | Prototyping web screens | HoaNK
5 | Construct code base source | NghiaNH
6 | Brainstorm requirements | All Members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Phases is moving a little slow | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Complete documentations | 2021-01-14
2 | Done reseaching the basic of used technologies | 2021-01-14
3 | Done web prototyping | 2021-01-14
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W2
PROJECT REPORT
Group | Journey
Week | 10/01/2021-14/01/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Research Project requirements | Completed | - Analyze Project requirements - Analyze technical solutions and methods to implements the functions - Research business logic bends requirements
2 | Research Project technologies | In Progress | - Final check on project's technologies - Research and implements test projects on project's technologies
3 | Work on documentation | Completed | - Finzlize general documentation. - Check the finished diagrams
4 | Prototyping web screens | Completed | - Finalize general web prototype - Fix the prototype to the analyzed requirements
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Screen Flow Diagrams | All Members | - School Admin: HoaNK,PhucNHH, NghiaNH - Student: AnhNDT, BaoPTL, HoaNK - Company Representative: NghiaNH, PhucNHH, AnhNDT
2 | Complete documentations | All Members | - Introduction: NghiaNH - Screen flow diagrams: All members - Screen Detail: AnhNDT - User Authorization: BaoPTL - Functional Requirements: All members - Backlog Detail: PhucNHH, BaoPTL
3 | Prototyping web screens | HoaNK & NghiaNH | - Finalizing general web design
5 | Construct code base source | NghiaNH | - Connstruct BE base code
6 | Brainstorm requirements | All Members | - Finalizing projects requirements
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Database Design and implements | 2021-01-21 | - ERD
2 | Done reseaching the basic of used technologies | 2021-01-21 | - implements researched technologies to pratical code
3 | implemts base functionalites | 2021-01-21 | - Login - Logout - Change password - Student List
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W3
PROJECT REPORT
Group | Journey
Week | 10/01/2021-14/01/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Research Project technologies | Completed | - Final check on project's technologies - Research and implements test projects on project's technologies
2 | Database Design and implements | Completed | - ERD
3 | Implemts base functionalites | In Progress | - Login - Logout - Change password - Student List
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Research Project technologies | All member | - Final check on project's technologies - Research and implements test projects on project's technologies
2 | Database Design and implements | NghiaNH, Bao | - ERD
3 | Implemts base functionalites | All member | - Login - Logout - Change password - Student List
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Software Design Document | 14/02/2022 | - Overview - Code design - Database Tables
2 | Complete implemts base functionalites | 18/02/2022 | - Login - Logout - Change password - Student List
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## W4
PROJECT REPORT
Group | Journey
Week | 10/01/2021-14/01/2021
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Complete implemts base functionalites | Completed | - Login - Logout
2 | Software Design Document | In Progress | - Overview - Code design - Database Tables
3
4
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Complete implemts base functionalites | All member | - Login - Logout
2 | Software Design Document | All member | - Overview - Code design - Database Tables
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Implements base funtionalites in Itergration 1 | 20/02/2022 | - View company list - View a specific company information - Edit a specific company information
2 | Complete Software Design Document | 20/02/2022 | - Overview - Code design - Database Tables
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C20: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue